## Sheet1
Project Backlog (January - May 2022)
Work Item | Assignee | Size Estimate | Priority | Sprint | Due Date | Story Point
Tech Proposal: AWS Services | Isabel | N/A | 1 | 12 | 2022-03-02 | 10
Tech Proposal: Affiliate Programs | Naeun | N/A | 10 | 14 | 2022-03-25 | 10
Tech Proposal: NHTSA | Jacob | N/A | 11 | 14 | 2022-03-25 | 4
Authentication | Naeun | Low | 2 | 12 | 2022-03-07 | 50
Authorization | Blake | Low | 3 | 12 | 2022-03-07 | 50
Log In / Log Out | Kayla | Low-Medium | 4 | 13 | 2022-03-07 | 60
Account Creation | Danny | Medium | 5 | 13 | 2022-03-07 | 60
Account Deletion | Jacob | Medium | 6 | 13 | 2022-03-07 | 60
Account Recovery | Isabel | Medium | 7 | 13 | 2022-03-07 | 60
Event Account Verification | Justin | Medium | 8 | 13 | 2022-03-07 | 60
Usage Analysis Dashboard | James | Medium-Large | 9 | 13 | 2022-03-07 | 80
Direct Message | Kayla | Medium-Large | 12 | 14-16 | 2022-04-20 | 100
Event List | Justin | Large | 13 | 14-16 | 2022-04-27 | 150
Part Flagging | Blake | Medium | 15 | 14-16 | 2022-05-02 | 80
Community Board | James | Large | 16 | 14-16 | 2022-05-02 | 160
Part Price Analysis | Jacob | Medium | 17 | 14-16 | 2022-05-02 | 100
Personalized Recommendations | Danny | Medium-Large | 18 | 14-16 | 2022-05-04 | 100
Notification System | Naeun | Medium-Large | 19 | 14-16 | 2022-05-04 | 100
Car Builder | Isabel | Large | 14 | 14-16 | 2022-05-07 | 140