## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Semester 1 (Fall)
MotoMoto
The New Panelists |  |  |  |  | Legend: | On track |  |  |  |  | Low Priority |  |  |  |  | Med Priority |  |  |  |  | High Priority |  |  |  |  | Unassigned
Blake Del Rey, Isabel Guzman, Jacob Sunia, James Austin Jr, Naeun Yu
Project Start Date: | 2021-08-24 |  |  |  |  | October | [20 empty] | November | [27 empty] | December
Scrolling Increment: | 51 | time axis 2021-10-14 to 2021-12-08
Sprint Description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
FALL SEMESTER
SPRINT 0
Proposal | Low Priority | James | 100% | 2021-08-30 | 38
SPRINT 1
Business Requirements Document | High Priority | Isabel | 90% | 2021-09-20 | 8
Tech Specs | Med Priority | Naeun | 80% | 2021-09-28 | 10
Site Map | Low Priority | Jacob | 100% | 2021-09-20 | 12
High Level Design Document | Med Priority | James | 100% | 2021-09-28 | 10
Milestone 1 | Milestone |  | 92.5% | 2021-10-06 | 1
SPRINT 2
Network Diagram | High Priority | James | 100% | 2021-10-15 | 6
Test Plan | High Priority | Jacob | 100% | 2021-10-15 | 6
SPRINT 3
Project Plan | High Priority | James | 100% | 2021-10-23 | 5
Project Road Map | Low Priority | Blake | 95% | 2021-10-23 | 5
Milestone 2 | Milestone |  | 98.75% | 2021-10-27 | 1 | bar: W
SPRINT 4
Tech Approvals | High Priority | James | 40% | 2021-10-30 | 5
Document Revision | Med Priority | James | 15% | 2021-10-30 | 5
SPRINT 5
Low Level Design | High Priority | Blake | 10% | 2021-11-06 | 5
Tech Approvals | Med Priority | James | 100% | 2021-11-06 | 5
SPRINT 6
Low Level Design | Med Priority | Blake | 10% | 2021-11-12 | 4
User Management | High Priority | Naeun | 100% | 2021-11-12 | 4
SPRINT 7
User Management | Med Priority | Naeun | 70% | 2021-11-17 | 6
Logging | High Priority | Jacob | 0% | 2021-11-17 | 6
Tech Approved | Goal |  | 70% | 2021-11-21 | 1 | S: 2
SPRINT 8
Logging | Med Priority | James | 0% | 2021-11-29 | 6
User Management | High Priority | Isabel | 0% | 2021-11-29 | 6
SPRINT 9
Low Level Design | High Priority | Blake | 0% | 2021-12-04 | 5
Document Revision | High Priority | Jacob | 0% | 2021-12-04 | 5
Documents Reviewed | Goal |  | 7.5% | 2021-12-07 | 1 | T: 2
Milestone 3 | Milestone |  | 48.33% | 2021-12-08 | 1 | bar: W

## Semester 2 (Spring)
MotoMoto
The New Panelists | [5 empty] | Legend: |  | On track |  |  |  |  | Low Priority |  |  |  |  | Med Priority |  |  |  |  | High Priority |  |  |  |  | Unassigned
Blake Del Rey, Isabel Guzman, Jacob Sunia, James Austin Jr, Naeun Yu, Justin Calma, Daniel Bribiesca, Kayla Chu
Project Start Date: | 2021-08-24 | [7 empty] | January | [13 empty] | February | [27 empty] | March
Scrolling Increment: | 147 | time axis 2022-01-18 to 2022-03-14
Sprint Description | Category | Assigned to | Estimated Hours | Progress | Start | End | Days |  | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
SPRING SEMESTER
SPRINT 10
Sprint Planning |  | James |  |  | 2022-01-26
Design |  |  | 50 hr
Implementation & Testing |  |  | 100 hr
Release |  |  | 10 hr |  | 2022-02-05 | 2022-02-06
Sprint Retrospective |  | James |  |  | 2022-02-07
Debug Logging, Archiving, User Management | Med Priority | Blake | 50 hr | 50% | 2022-01-26 | 2022-02-06 | 11
Optimize Logging, Archiving, User Management | Low Priority | Jacob | 50 hr | 50% | 2022-01-26 | 2022-02-06 | 11
Security: Authentication and Authorization | Med Priority | Naeun | 35 hr | 1% | 2022-01-26 | 2022-02-06 | 11
Update Deliverables (Project Plan, BRD, Site Map) | High Priority | Daniel | 25 hr | 80% | 2022-01-26 | 2022-02-06 | 11
Document Updated | Goal |  |  | 60% | 2022-02-05 | 2022-02-06 | 1 |  | S: 2
SPRINT 11
Sprint Planning |  | James |  |  | 2022-02-07
Design |  |  | 100 hr
Implementation & Testing |  |  | 200 hr
Release |  |  | 20 hr |  | 2022-02-19 | 2022-02-20
Sprint Retrospective |  | James |  |  | 2022-02-20
Account Creation | High Priority | Daniel | 65 hr | 0% | 2022-02-06 | 2022-02-20 | 14
Account Deletion | Med Priority | Jacob | 50 hr | 0% | 2022-02-06 | 2022-02-20 | 14
Account Recovery | Med Priority | Isabel | 25 hr | 0% | 2022-02-06 | 2022-02-20 | 14
Authentication & Authorization | Med Priority | Blake | 40 hr | 0% | 2022-02-06 | 2022-02-20 | 14
Community Board | Med Priority | James | 90 hr | 0% | 2022-02-06 | 2022-02-20 | 14
Event List | Med Priority | Justin | 60 hr | 0% | 2022-02-06 | 2022-02-20 | 14
Direct Message | Low Priority | Kayla | 30 hr | 0% | 2022-02-06 | 2022-02-20 | 14
Team Review | On Track |  |  |  | 2022-02-20 | 2022-02-26 | 6
SPRINT 12
Sprint Planning |  |  |  |  | 2022-02-21
Design |  |  | 50 hr
Implementation & Testing |  |  | 100 hr
Release |  |  | 10 hr |  | 2022-02-28 | 2022-03-01
Sprint Retrospective |  |  |  |  | 2022-03-02
Log Out | High Priority | Naeun | 30 hr | 0% | 2022-02-21 | 2022-03-01 | 8
Event Account Verification | High Priority | Blake | 35 hr | 0% | 2022-02-21 | 2022-03-01 | 8
Community Board: Main Feed | High Priority | James | 25 hr | 0% | 2022-02-21 | 2022-03-01 | 8
Event List: Event Hosting | Med Priority | Justin | 20 hr | 0% | 2022-02-21 | 2022-03-01 | 8
Car Builder: Main Menu | Med Priority | Isabel | 25 hr | 0% | 2022-02-21 | 2022-03-01 | 8
Direct Message: Encryption | Low Priority | Kayla | 25 hr | 0% | 2022-02-21 | 2022-03-01 | 8
Event List | Goal |  |  | 0% | 2022-02-28 | 2022-03-01 | 1 |  | M: 2
Community Board | Goal |  |  | 0% | 2022-02-28 | 2022-03-01 | 1 |  | M: 2
SPRINT 13
Sprint Planning |  |  |  |  | 2022-03-02
Design |  |  | 50 hr
Implementation & Testing |  |  | 100 hr
Release |  |  | 10 hr |  | 2022-03-09 | 2022-03-10
Sprint Retrospective |  |  |  |  | 2022-03-11
User Privacy | High Priority | Kayla | 30 hr | 0% | 2022-03-02 | 2022-03-10 | 8
Part Flagging: Flag Registry | High Priority | Jacob | 35 hr | 0% | 2022-03-02 | 2022-03-10 | 8
Part Flagging: Car Builder | Med Priority | Naeun | 35 hr | 0% | 2022-03-02 | 2022-03-10 | 8
Personalized Recommendations | Low Priority | Daniel | 35 hr | 0% | 2022-03-02 | 2022-03-10 | 8
Notification System | Low Priority | Naeun | 25 hr | 0% | 2022-03-02 | 2022-03-10 | 8
Direct Message | Goal |  |  | 0% | 2022-03-10 | 2022-03-11 | 1
Team Code Review | On Track | Everyone |  | 18% | 2022-03-06 | 2022-03-19 | 13
SPRINT 14
Sprint Planning |  |  |  |  | 2022-03-11
Design |  |  | 60 hr
Implementation & Testing |  |  | 120 hr
Release |  |  | 20 hr |  | 2022-03-23 | 2022-03-24
Sprint Retrospective |  |  |  |  | 2022-03-25
Car Builder: Affiliate Program Integration | High Priority | Jacob | 60 hr | 0% | 2022-03-11 | 2022-03-25 | 14
Personalized Recommendations: Main Feed Integration | Med Priority | Daniel | 40 hr | 0% | 2022-03-11 | 2022-03-25 | 14
Notification System: Out-App (Email) Notifications | Med Priority | Naeun | 20 hr | 0% | 2022-03-11 | 2022-03-25 | 14
Notification System: In-App Notification | Med Priority | Naeun | 20 hr | 0% | 2022-03-11 | 2022-03-25 | 14
Part Price Analysis | Low Priority | Blake | 60 hr | 0% | 2022-03-11 | 2022-03-25 | 14
Personalized Recommendations | Goal |  |  | 0% | 2022-03-10 | 2022-03-11 | 1
Car Builder | Goal |  |  | 0% | 2022-03-10 | 2022-03-11 | 1
Milestone 5 | Milestone |  |  |  | 2022-03-27 | 2022-03-28 | 1
SPRINT 15
Sprint Planning |  |  |  |  | 2022-04-05
Design |  |  | 50 hr
Implementation & Testing |  |  | 100 hr
Release |  |  | 10 hr |  | 2022-04-13 | 2022-04-14
Sprint Retrospective |  |  |  |  | 2022-04-15
Car Builder: Part Flags | High Priority | James | 60 hr | 0% | 2022-04-05 | 2022-04-15 | 10
Part Price Analysis: Community Board Integration | Med Priority | Blake | 40 hr | 0% | 2022-04-05 | 2022-04-15 | 10
Notification System: In-App Notification | Med Priority | Naeun | 20 hr | 0% | 2022-04-05 | 2022-04-15 | 10
Notification System: Out-App (Email) Notifications | Med Priority | Naeun | 20 hr | 0% | 2022-04-05 | 2022-04-15 | 10
Event Account Verfication: Event List Integration | Low Priority | Justin | 20 hr | 0% | 2022-04-05 | 2022-04-15 | 10
Part Flagging | Goal |  |  | 0% | 2022-04-16 | 2022-04-17 | 1
Part Price Analysis | Goal |  |  | 0% | 2022-04-16 | 2022-04-17 | 1
Team Review | On Track |  |  |  | 2022-04-10 | 2022-04-16 | 6
SPRINT 16
Sprint Planning |  |  |  |  | 2022-04-18
Design |  |  | 20 hr
Implementation & Testing |  |  | 130 hr
Release |  |  | 10 hr |  | 2022-04-29 | 2022-04-30
Sprint Retrospective |  |  |  |  | 2022-05-03
Notification System: Community Board Integration | Med Priority | James | 40 hr | 0% | 2022-04-17 | 2022-05-01 | 14
Notification System: Event List Integration | Med Priority | Justin | 40 hr | 0% | 2022-04-17 | 2022-05-01 | 14
Notification System: Personalized Recommendations Integration | Med Priority | Daniel | 40 hr | 0% | 2022-04-05 | 2022-04-15 | 10
Notification System: Part Flags Integration | Med Priority | Jacob | 40 hr | 0% | 2022-04-05 | 2022-04-15 | 10
Notification System | Goal |  |  | 0% | 2022-05-01 | 2022-05-02 | 1
Milestone 6 | Milestone |  |  |  | 2022-05-02 | 2022-05-03 | 1
Code Revision | High Priority | Everyone |  | 0% | 2022-04-17 | 2022-05-07 | 20
All Code Reviewed | Goal |  |  | 0% | 2022-05-05 | 2022-05-06 | 1
Final Day | Milestone |  |  |  | 2022-05-06 | 2022-05-07 | 1
Formulas:
Legend: = SUM(Milestones4353[[#This Row],[Start]],Milestones4353[[#This Row],[Days]])
Legend: = SUM(Milestones4353[[#This Row],[Start]], Milestones4353[[#This Row],[Days]])

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low priority |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-02-05 |  |  |  |  | July | [27 empty] | August
Scrolling Increment: | 149 | [59 empty] | 2022-08-28 | time axis 2022-07-04 to 2022-08-27
Milestone description | Category | Assigned to | Progress | Start | Days | [55 empty] | S | time axis 2022-07-04 to 2022-08-27
TITLE 1 | Low Priority
Task 1 | Goal | Name | 25% | 2022-02-05 | 3
Task 2 | Milestone |  |  | 2022-02-10 | 1
Task 3 | Low Priority |  | 50% | 2022-02-02 | 10
Task 4 | On Track |  |  | 2022-02-25 | 3
Task 5 | Med Risk |  | 10% |  | 6
TITLE 2
Task 1 | High Priority |  | 60% | 2022-02-11 | 13
Task 2 | On Track |  | 50% | 2022-02-13 | 9
Task 3 | Low Priority |  | 33% | 2022-02-18 | 11
Task 4 | Milestone |  |  | 2022-02-20 | 1
Task 5 | Low Priority |  |  | 2022-02-21 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-02-20 | 4
Task 2 | Med Risk |  |  | 2022-02-23 | 14
Task 3 | On Track |  |  | 2022-03-10 | 6
Task 4 | Goal |  |  | 2022-03-14 | 3
Task 5 | Low Risk |  |  | 0 | 19
TITLE 4
Task 1 |  |  |  | 2022-03-17 | 15
Task 2 |  |  |  | 2022-03-31 | 5
Task 3 | Milestone |  |  | 2022-05-12 | 1
Task 4
Task 5
Med Priority
Task 5 | Low Priority |  | 50% | 2021-10-25 | 20

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-02-05 |  |  |  |  | February | [20 empty] | March
Scrolling Increment: | 5 | time axis 2022-02-10 to 2022-04-06
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-02-10 to 2022-04-06
TITLE 1
Task 1 | Goal | Name | 25% | 2022-02-05 | 3
Task 2 | Milestone |  |  | 2022-02-10 | 1 | bar: 2022-02-10
Task 3 | Low Risk |  | 50% | 2022-02-02 | 10
Task 4 | Milestone |  |  | 2022-02-25 | 1 | bar: 2022-02-25
Task 5 | Med Risk |  | 10% | 2022-02-11 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-02-11 | 13
Task 2 | On Track |  | 50% | 2022-02-13 | 9
Task 3 | Low Risk |  | 33% | 2022-02-18 | 11
Task 4 | Milestone |  |  | 2022-02-20 | 1 | bar: 2022-02-20
Task 5 |  |  |  | 2022-02-21 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-02-20 | 4
Task 2 | Med Risk |  |  | 2022-02-23 | 14
Task 3 | On Track |  |  | 2022-03-10 | 6
Task 4 | Goal |  |  | 2022-03-14 | 3 | 2022-03-14: 2; 2022-03-15: 2; 2022-03-16: 2
Task 5 | Low Risk |  |  | 2022-02-11 | 19
TITLE 4
Task 1 |  |  |  | 2022-03-17 | 15
Task 2 |  |  |  | 2022-03-31 | 5
Task 3 | Milestone |  |  | 2022-05-12 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one